## CaseStudy-1
Case Study 1: Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration | Start Offset | Progress | Completed | InProgress | Pending
T1 | Requirement Gathering | 2026-09-01 | 2026-09-05 | 5 | 6 | 100% | 5 | 0 | 0
T2 | Requirement Analysis | 2026-09-06 | 2026-09-10 | 5 | 11 | 100% | 5 | 0 | 0
T3 | UI/UX Design | 2026-09-11 | 2026-09-18 | 8 | 16 | 100% | 8 | 0 | 0
T4 | Frontend Development | 2026-09-19 | 2026-09-30 | 12 | 24 | 50% | 6 | 6 | 0
T5 | Backend Development | 2026-09-25 | 2026-10-08 | 14 | 30 | 0% | 0 | 0 | 14
T6 | Testing | 2026-10-09 | 2026-10-15 | 7 | 44 | 0% | 0 | 0 | 7
T7 | Deployment | 2026-10-16 | 2026-10-18 | 3 | 51 | 0% | 0 | 0 | 3
The longest task is Backend Development.
The Tasks that overlap is Frontend Development (Last Half) & Backend Development (First Half).
The total project duration - 54 days.

## Case Study 2
Case Study 2: Sales Monthly Trend Line
Month | Sales (₹) | Sales Forecast(₹) | Row Labels | Sum of Sales (₹) | Sum of Sales Forecast(₹)
2026-01-01 | 45000 |  | 2026 | 766000
2026-02-01 | 48000 |  | Jan | 45000
2026-03-01 | 52000 |  | Feb | 48000
2026-04-01 | 55000 |  | Mar | 52000
2026-05-01 | 58000 |  | Apr | 55000
2026-06-01 | 62000 |  | May | 58000
2026-07-01 | 65000 |  | Jun | 62000
2026-08-01 | 69000 |  | Jul | 65000
2026-09-01 | 72000 |  | Aug | 69000
2026-10-01 | 76000 |  | Sep | 72000
2026-11-01 | 80000 |  | Oct | 76000
2026-12-01 | 84000 |  | Nov | 80000
2027-01-01 |  | 86786.7381 | Dec | 84000
2027-02-01 |  | 90493.34 | 2027 |  | 685730.4616
2027-03-01 |  | 93746.4893 | Jan |  | 86786.7381
2027-04-01 |  | 97751.6768 | Feb |  | 90493.34
2027-05-01 |  | 101638.3042 | Mar |  | 93746.4893
2027-06-01 |  | 105470.0854 | Apr |  | 97751.6768
2027-07-01 |  | 109843.8279 | May |  | 101638.3042
|  |  | Jun |  | 105470.0854
|  |  | Jul |  | 109843.8279
|  |  | Grand Total | 766000 | 685730.4616
Business Insights:
The sales trend is increasing.
The month with the highest actual sales Dec 2026 with ₹84000.
Q. What does this forecast mean for Management?
Ans:- Forecasting means estimating future business outcomes based on historical data and current trends. For management, it helps in better planning, budgeting, and decision-making. It reduces uncertainty and helps the company prepare for future risks and opportunities.

## Forecast Sheet
Month | Sales (₹) | Forecast(Sales (₹))
2026-01-01 | 45000
2026-02-01 | 48000
2026-03-01 | 52000
2026-04-01 | 55000
2026-05-01 | 58000
2026-06-01 | 62000
2026-07-01 | 65000
2026-08-01 | 69000
2026-09-01 | 72000
2026-10-01 | 76000
2026-11-01 | 80000
2026-12-01 | 84000 | 84000
2027-01-01 |  | 87905.3807
2027-02-01 |  | 91990.4853
2027-03-01 |  | 96075.59
2027-04-01 |  | 100160.6947
2027-05-01 |  | 104245.7994
2027-06-01 |  | 108330.9041
2027-07-01 |  | 112416.0087

## CaseStudy-3
Case Study 3: What-If Analysis and Scenario Manager
Particular | Value | Scenario | Sales | Expenses | Profit
Sales | 450000 | Best Case | 800000 | 350000 | 450000
Expenses | 450000 | Normal Case | 600000 | 400000 | 200000
Profit | 0 | Worst Case | 450000 | 450000 | 0
Business Insights:
The scenario with the highest profit is Best Case with ₹4,50,000 profit.
The scenario with the greatest business risk is Worst Case with ₹0.

## Scenario Summary
Scenario Summary
|  | Current Values: | Normal Case | Best Case | Worst Case
|  |  | Created by Jeisa Mathew on 22-08-2026 | Created by Jeisa Mathew on 22-08-2026 | Created by Jeisa Mathew on 22-08-2026
Changing Cells:
| $C$3 | 600000 | 600000 | 800000 | 450000
| $C$4 | 400000 | 400000 | 350000 | 450000
Result Cells:
| $C$5 | 200000 | 200000 | 450000 | 0
Notes: Current Values column represents values of changing cells at
time Scenario Summary Report was created. Changing cells for each
scenario are highlighted in gray.

## CaseStudy-4
Case Study 4: Compare Different Business Scenarios
Scenario | Sales | Fixed Expenses | Variable Cost % | Marketing Cost | Variable Cost | Total Expenses | Profit | Profit Margin %
Best Case | 900000 | 200000 | 40% | 80000 | 360000 | 640000 | 260000 | 28.8889
Normal Case | 700000 | 200000 | 50% | 60000 | 350000 | 610000 | 90000 | 12.8571
Worst Case | 500000 | 220000 | 60% | 50000 | 300000 | 570000 | -70000 | -14
| Row Labels | Sum of Profit
| Best Case | 260000 |  |  | Row Labels | Sum of Sales | Sum of Total Expenses
| Normal Case | 90000 |  |  | Best Case | 900000 | 640000
| Worst Case | -70000 |  |  | Normal Case | 700000 | 610000
| Grand Total | 280000 |  |  | Worst Case | 500000 | 570000
[5 empty] | Grand Total | 2100000 | 1820000
Business Insights:
The scenario with the highest sales - Best Case.
The scenario with the highest profit - Best Case.
The scenario with the highest expenses - Best Case.
The scenario with the highest profit margin - Best Case.
Q: Explain what happens to profit when sales decrease.
Ans: - When sales decrease, profit also decreases — and falls even faster than sales, because fixed expenses don't reduce proportionately. This is seen in the Worst Case, where sales dropped to 500,000 and expenses stayed relatively high (570,000), resulting in a loss of -70,000.
Q: Explain what happens when the variable cost percentage increases.
Ans:- When the variable cost percentage increases, Variable Cost rises even if sales stay flat, pushing up Total Expenses and reducing Profit. This is seen across the scenarios, where variable cost % rises from 40% (Best Case) to 60% (Worst Case), and Profit falls correspondingly from 260,000 to -70,000.
Q: Recommend one scenario to management and explain why
Ans: - The Best Case scenario is recommended to management. It has the highest Sales (900,000), lowest variable cost % (40%), highest Profit (260,000), and the strongest Profit Margin (28.89%), making it the most efficient and profitable outcome to target.